| PLASTIBIOFUEL | FORMS AND CERTIFICATIONS |
| --- | --- |

DOE SBIR/STTR FY26 PHASE I  ·  GENESIS MISSION

Nothing to sign

at the pitch stage

DOE requires no forms, certifications, or representations at the pitch stage. The only gate is an AMP account. Stage 2 applies only if the pitch is invited forward, and DOE has not yet published the full-application forms package. Every Stage 2 row is marked by source so nothing anticipated is mistaken for something confirmed.

| CONFIRMED Stated on a DOE or ConnectWerx page as of August 22, 2026 | ANTICIPATED Standard SBIR/STTR practice, not yet published here |
| --- | --- |

| STAGE 1 · PITCH | Due Sep 10, 2026, 2:00 PM ET |
| --- | --- |

| REQUIRED | AMP account request WHERE register.ati.org ¦ SIGNS Michael Ward, no signature Required before submission. Under 5 minutes to request, allow 1 to 2 business days for approval. |
| --- | --- |

| READY | Pitch submission form, four open-text answers WHERE AMP, sbirsttr-amp.ati.org ¦ SIGNS No signature Text is written. See the Pitch Responses document in this package. |
| --- | --- |

| REQUIRED | Topic selection, one only WHERE AMP submission form ¦ SIGNS No signature Topic 1, Scaling the Biotechnology Revolution. Cannot be changed after submission. |
| --- | --- |

| OPTIONAL | Bibliography and References Cited WHERE AMP file upload, PDF, 5 MB or smaller ¦ SIGNS No signature Prepared. Upload the file named PlastiBioFuelBibliography.pdf. |
| --- | --- |

| NOT APPLICABLE | Certifications and representations WHERE Not applicable ¦ SIGNS Not applicable None required at pitch stage. Confirmed against the ConnectWerx opportunity page and FAQ on August 22, 2026. |
| --- | --- |

| NOT APPLICABLE | SBIR versus STTR election WHERE Not applicable ¦ SIGNS Not applicable Not made at pitch. DOE states pitches are not evaluated separately for SBIR and STTR. |
| --- | --- |

| STAGE 2 · FULL APPLICATION | Only if invited |
| --- | --- |

| CONFIRMED | Active SAM.gov registration and UEI WHERE sam.gov/entity-registration ¦ SIGNS Michael Ward as Entity Administrator UEI KQAWZ54RDUM8 must be entered on the application. |
| --- | --- |

| CONFIRMED | SBA Company Registry registration and proof WHERE app.www.sbir.gov/company-registration ¦ SIGNS Michael Ward Proof of registration is required as part of the application. |
| --- | --- |

| CONFIRMED | Small Business Concern eligibility representation WHERE Full application ¦ SIGNS Michael Ward, Founder and CEO For-profit, U.S. place of business, 51 percent or more U.S. citizen owned and controlled, 500 or fewer employees. Form not yet published. |
| --- | --- |

| CONFIRMED | Place of performance WHERE Full application ¦ SIGNS Michael Ward All research and development performed in the United States. |
| --- | --- |

| CONFIRMED | SBIR only: PI primary employment certification WHERE Full application ¦ SIGNS Michael Ward as PI More than 50 percent employment with the small business. |
| --- | --- |

| CONFIRMED | SBIR only: work-share certification WHERE Full application ¦ SIGNS Michael Ward Small business performs at least two-thirds of Phase I effort. |
| --- | --- |

| CONFIRMED | STTR only: work-share certification WHERE Full application ¦ SIGNS Michael Ward and UNT authorized official Small business at least 40 percent and research institution at least 30 percent. |
| --- | --- |

| CONFIRMED | STTR only: written IP allocation and licensing agreement WHERE Executed before work begins ¦ SIGNS Michael Ward and UNT authorized official DOE states this must be in place before work begins. |
| --- | --- |

| ANTICIPATED | Essentially equivalent work and duplicate funding disclosure WHERE Full application ¦ SIGNS Michael Ward Standard across SBIR and STTR agencies. Ready-to-use language is below. |
| --- | --- |

| ANTICIPATED | Current and pending support for all personnel WHERE Full application ¦ SIGNS Michael Ward Not yet published for this opportunity. |
| --- | --- |

| ANTICIPATED | UNT subaward statement of work and budget WHERE Full application attachment ¦ SIGNS Prepared by PlastiBioFuel with UNT input Award-stage under 2 CFR 200.332. Institutional sign-off is not required at submission. |
| --- | --- |

| ANTICIPATED | Budget and line-by-line justification WHERE Full application ¦ SIGNS Michael Ward Must not exceed $250,000, or $256,500 with TABA. |
| --- | --- |

| ANTICIPATED | Foreign risk management and research security disclosures WHERE Full application ¦ SIGNS Michael Ward DOE maintains a Foreign Risk Management page for the SBIR and STTR programs. |
| --- | --- |

DUPLICATE FUNDING DISCLOSURE, READY TO USE Use this wording on any essentially equivalent work certification at full application. It is already reflected in Question 4 of the pitch. “PlastiBioFuel LLC has one other federal proposal pending: NSF SBIR Phase I, Research.gov proposal 328095, solicitation NSF 26-510, subtopic BT10 Synthetic Biology and Metabolic Engineering, total requested $304,955, submitting against the November 4, 2026 window. That proposal addresses COF-enzyme reusability, the monomer-to-ethanol biological conversion pathway, and construction of an integrated lab-scale spiral reactor module. The scope proposed to DOE is the computational design layer: a physics-informed machine learning surrogate model of the immobilized-enzyme reactor and its experimental validation. The two efforts share no tasks, no personnel effort months, and no budget lines. This is not essentially equivalent work, and no duplicate funding would result from award of both.”

TWO STANDING RULES FOR THIS PACKAGE 1. Dr. Shengqian Ma is Other Personnel on NSF-style forms, not Senior or Key Personnel. DOE has not published its personnel categories for this opportunity, so apply the same treatment unless the DOE form defines categories differently. 2. ARG Petro is offtake discussions and interest. There is no signed letter of intent and no executed offtake agreement. No document in this package may say otherwise.

| PlastiBioFuel LLC · SDVOSB, SBA VetCert verified · NAICS 325199, 325193, 541715 | UEI KQAWZ54RDUM8 · CAGE 175D6 |
| --- | --- |